## Redacted web version 2025
2025-2026 Annual Work Plan - TWG on Ending Childhood Statelessness (3/23/2026)
Vision | End discrimination in nationality laws and policies
Mission | Advancing equal rights by eliminating discriminatory nationality laws, including based on gender, to prevent statelessness and ensure that all women, children, and families fully enjoy their fundamental rights to citizenship under international standards.
Axe 1: Awareness Raising
Output 1 | Lead | Activities and Tasks | Timeframe
1.1 Produce innovative knowledge on discriminatory nationality laws and policies | TWG Co-Chairs and Members | 1.1.1 "Country spotlights" to showcase momentum for reform | October 2025 January 2026
| TWG Co-Chairs and Members | 1.1.2 Testimonials of impacted persons | September 2025 November 2025 May 2026
| TWG Co-Chairs and Members | 1.1.3 One-page brief on gender discrimination in nationality laws, linking to other resources | March 2026
| TWG Co-Chairs and Members | 1.1.4 Thematic Working Group 2026 Knowledge Webinar | October 2026
1.2 Host public events to promote alliance and raise awareness of discrimination in nationality laws and policies | TWG Co-Chairs and Members | 1.2.1 Webinar for the alliance | December 2025
| TWG Co-Chairs and Members | 1.2.2 Public event at CSW70 with high-level speakers | March 2026
1.3 Leverage social media for collaborative public outreach | TWG Co-Chairs and Members | 1.3.1 Use key international days to promote reform of disriminatory nationality laws and policies (e.g., HLPF, Human Rights Day, 16 Days of Activism, etc.) | Ongoing
| TWG Co-Chairs and Members | 1.3.2 Working group members integrate awareness raising into other forums/advocacy opportunities as they arise | Ongoing
Axe 2: Capacity Building
Output 2 | Lead | Activities and Tasks | Timeframe
2.1 Work with target governments, ministries, and civil society organizations to formulate action plans for reform of discriminatory nationality laws and policies | TWG Co-Chairs and Members | 2.1.1 Post-Summit on Advancing Gender Equality in Nationality Laws Participant Roundtable | July 2025
| TWG Co-Chairs and Members | 2.1.2 Gulf Regional Multistakeholder Convening | October 2025
| TWG Co-Chairs and Members | 2.1.3 Africa Multistakeholder Convening | February 2026
| TWG Co-Chairs and Members | 2.1.4 Regional online roundtable with intergovernmental organization and Member States | June 2026
| TWG Co-Chairs and Members | 2.1.5 Thematic sessions in Alliance Regional Network Labs | TBC
| TWG Co-Chairs and Members | 2.1.6 Asia Multistakeholder Convening | November/December 2026
2.2 Enhance solidarity, sharing of lessons learned and collaborative planning on advocacy initiatives by Thematic Working Group and impacted persons | TWG Co-Chairs and Members | 2.2.1 Capacity building roundtables for TWG | November 2025 April 2026
| TWG Co-Chairs and Members | 2.2.2 Impacted Person Convenings (3/year, GCENR organized) | October 2025 February 2026 May 2026